To ensure this proposal maintains its professional formatting when pasted into Microsoft Word, I have converted the Markdown into a structured document layout.

How to Use This

- Select All of the text below.

- Copy (Ctrl+C) and Paste into a new MS Word document (Ctrl+V).

- Word Styling Tip: I recommend highlighting the main section headers (e.g., "Technical Specialties") and applying the Heading 2 style from the Word ribbon. This will allow you to generate an automated Table of Contents instantly.

Proposal: Cloud ERP Implementation & WMS Integration

Prepared for: Nexus Global Logistics

RFP Reference Number: NGL-2026-ERP-04

Submission Deadline: May 20, 2026, 5:00 PM EST

Prepared by: Acme Solutions

Date: May 2026

Company Information

- Company Name: Acme Solutions

- Headquarters: 123 ABC Lane, St. Louis, MO 63105

- Years in Business: Founded in 2014 (11+ years of continuous operation)

Primary Contact

James O'Brien

VP of Sales & Partnerships

- Email: [PLACEHOLDER]

- Phone: [PLACEHOLDER]

James brings 15 years of experience in B2B enterprise software sales and manages Acme Solutions' strategic alliances with AWS, Microsoft, and SAP.

Technical Specialties and Certifications

Technical Specialties

- Enterprise Software Integration: Expertise in REST, GraphQL, gRPC, SOAP, and EDI. Pre-built connectors for SAP S/4HANA, Oracle NetSuite, and Salesforce.

- Cloud Modernization: 280+ architects experienced in AWS, Azure, and GCP.

- Messaging & Middleware: Production experience with Apache Kafka, AWS SQS/SNS, and Azure Service Bus.

- Security: Full support for OAuth 2.0/OIDC, SAML 2.0, and mTLS.

SAP Partnership Status

Acme Solutions is a top-tier SAP partner. This elite status provides early access to product roadmaps and priority escalation channels with SAP engineering. Our consultants hold professional certifications in Finance (FI), Controlling (CO), and Materials Management (MM).

Compliance Attestations

| Certification | Status | Relevance |
| --- | --- | --- |
| ISO 27001 | Certified | Information security for all data handling |
| SOC 2 Type II | Certified | Annual independent audit of security controls |
| AWS Advanced Partner | Active | Cloud infrastructure expertise |

High-Level Approach Synopsis

Acme Solutions utilizes a phased delivery model with four foundational pillars:

- Discovery & Assessment: Stakeholder interviews and current-state architecture review (SQL systems to Manhattan Active WMS).

- Design & Configuration: ERP tenant configuration using SAP Activate methodology.

- Integration & Migration: Bidirectional API build for real-time inventory and billing sync, plus secure ETL of 10 years of financial history.

- Testing & Hypercare: UAT, knowledge transfer, and 90-day post-go-live support.

Project Management Methodology

We propose a Hybrid Methodology—combining Waterfall's governance with Agile’s iterative delivery velocity.

- Waterfall Governance: Phase-gate approvals, milestone-driven timelines, and a formal change control process.

- Agile Execution: 2-week sprints, weekly demos, and automated CI/CD pipelines.

Risk Mitigation & Business Continuity

To ensure zero disruption to warehouse operations during the WMS API integration:

- Sandbox Isolation: No untested code touches production; development occurs in mirrored environments.

- Parallel Operation: Running legacy and new systems concurrently with continuous data reconciliation.

- Circuit Breakers: Integration architecture that automatically isolates failing endpoints to prevent cascading failures.

- Rollback Procedures: Tested cutover runbooks with defined Recovery Time Objectives (RTO).

Data Migration Approach

Acme will migrate 10 years of historical financial data from legacy SQL databases to SAP S/4HANA.

- Tooling: SQL Server Integration Services (SSIS) for ETL and Power BI for data quality dashboards.

- Security Standards: AES-256 encryption at rest, TLS 1.3 in transit, and immutable audit logging.

- Validation: Row-count reconciliation, checksum validation, and stakeholder sign-off on sample data sets.

Proposed Project Timeline

Anticipated Kickoff: July 1, 2026

| Phase | Duration | Target End Date |
| --- | --- | --- |
| 1. Discovery & Roadmap | 4 Weeks | July 31, 2026 |
| 2. ERP Configuration | 10.5 Weeks | October 15, 2026 |
| 3. Migration & Integration | 9 Weeks | November 15, 2026 |
| 4. Testing & UAT | 4 Weeks | November 30, 2026 |
| 5. Training & Go-Live | 2 Weeks | December 15, 2026 |
| 6. Hypercare Support | 90 Days | March 15, 2027 |

Itemized Pricing (Time & Materials)

| Description | Estimated Hours | Rate (USD) | Total |
| --- | --- | --- | --- |
| Roadmap | 250 | $150.00 | $37,500.00 |
| Configure ERP Tenant | 1,000 | $150.00 | $150,000.00 |
| API Integration | 600 | $150.00 | $90,000.00 |
| Testing | 200 | $150.00 | $30,000.00 |
| Subtotal |  |  | $307,500.00 |
| Margin (28%) |  |  | $86,100.00 |
| Grand Total |  |  | $393,600.00 |

T&E costs for on-site work will be provided as a separate capped amount (estimated $25k–$50k).

Authorized Signatory Confirmation

Acme Solutions confirms that all information in this proposal is accurate and that our ISO 27001 and SOC 2 Type II certifications remain in good standing.

Signature: ___________________________

Printed Name: [PLACEHOLDER]

Date: ___________________________

Acme Solutions | 123 ABC Lane, St. Louis, MO 63105 | RFP Reference: NGL-2026-ERP-04